7

DISH23.0 Project Implementation Plan

FOR DISH23.0 IMPLEMENTATION

Rev. 1

July 2018

IATA Document Revision and Distribution History Revision History Revision Date; Summary of Changes; Revision #. July 2018; NA; 0. August 2018; - Update Figure with milestones in section 3 - Update RPSI table in section 5.1 - Update 13.1.4 - Update 13.1.5 - Update Table in section 5.1; 1. February 2019; - Typos; 2-3. April 2019; - New Go Live dates for Wave 3 pilot BSPs BR and ZA - New Go Live Dates for non-pilot BSPs to accommodate first date of Billing Period; 4-5-6. May 2019; - Update Go Live dates for Pilot BSPs; 7. June 2019; - Typo page 27 – Go live dates BR and ZA; 8. August 2019; - Introduce the Trinidad / Tobago split BSPs; 9. Supervision History Revision #; Revision Date; Document Reviewed. 1; N/A; IATA. Distribution History Revision #; Revision Date; Document Distribution. 1; July 2018. 2; August 2018. 3; February 2019. 4; April 2019. 5; April 2019. 6; April 2019. 7; May 2019. 8; June 2019. 9; August 2019. Document Owner Owner; IATA. Author; IATA.

Content

1.	Objective	6

2.	Background	7

2.1	What is DISH Standard?	7

2.2	What is DISH23.0 Standard?	7

3.	IATA´s approach to DISH23.0 implementation	9

3.1	DISH23.0 implementation Team	9

4.	Partners/Stakeholders In-Scope	10

5.	Pilot Test BSPs	11

5.1	Pilot Test BSPs	11

5.1.1	Pilot Test Scope	12

5.2	Test Plan for Pilot BSPs	12

6.	Reporting Systems Involvement	13

6.1	Global Reporting Systems Readiness Milestone	13

6.2	Input Test Files per Reporting System	13

6.3	Card Authentication and 3DS Card Authentication Information (IT0D and IT0X Records)	13

6.4	Test Period (SPED)	13

6.5	Test File Naming Convention	14

6.6	Test File Delivery Method	14

6.7	RET/TI Testing Methodology	14

7.	DPCs Involvement	16

7.1	DPCs Readiness Milestone	16

7.2	RET/TI Validation & Processing	16

7.3	Airline HOT Generation	16

7.3.1	Pilot BSPs	16

7.3.2	Non-Pilot BSPs	16

7.4	Airline CSI Generation	16

7.5	Card Acquirers CSI Generation	17

7.6	Agent HOT Generation	17

8.	Airlines Involvement	18

8.1	HOT files testing	18

8.2	Airline CSI files testing	18

8.3	RET files from Airlines (WebLink)	19

8.4	RET files from Airlines (NDCLink)	19

9.	Acquirers Involvement	20

9.1	Acquirers CSI files testing	20

10.	Agents Involvement	22

10.1	Agent HOT files testing	22

11.	Third Parties Involvement	23

12.	IATA Involvement	24

13.	Implementation Schedule	25

13.1	Milestones and Timelines	25

13.1.1	Testing Process	25

13.1.2	Sign-Off Date and Go/No-Go Decision	26

13.1.3	Implementation Date	26

13.1.4	Pilot BSPs	26

13.1.5	Global Roll-Out BSPs	27

14.	APPENDIX A: 3DS TEST	29

Objective

The objective and purpose of this document is to provide information related to:

- DISH23.0 implementation and testing scope for both, pilot waves and production/global roll out waves respectively including time-scales

- Engagement with all stakeholders and business partners to successfully deliver the DISH23 project

- Coordination with all stakeholders and business partners to successfully certify DISH23 new reporting capabilities in their systems

Background

What is DISH Standard?

Data Interchange Specifications Handbook (DISH) is the global data interchange standard implemented by all BSPs, to ensure consistency and the exchange of the highest possible quality data between BSPs, GDSs, airlines and other business partners

To support the reporting of Passenger sales and ticketing data for settlement purposes, the DISH provides the passenger travel industry with a set of standard formats:

- Agent Reporting (RET) - agents reporting via the Global Distribution Systems (GDSs) to the BSP

- Airline Accounting/Sales (HOT) - hand off transmission and accounting data file from the BSP

- Credit Sales Invoicing (CSI) - transactions produced by the BSP for the credit card company or airline

- Ticket Inventory Data (TI) - allocation of STD numbers to BSPs, ticketing systems and airlines

- IATA Credit Card Settlement Plan (CSP) – invoicing file with card transactions, consolidated daily, to whichever acquirers are nominated by the individual Airline members of CCSP

What is DISH23.0 Standard?

The Passenger Services Conference (PSC) endorsed Revision 23 of the DISH and has declared it effective as of 1 April 2018. This revision represents important upgrades and enhancements as well as new reporting functions which will benefit the Business partners as outlined below:

- Addition of 3DS and EMV data elements and records for card transactions

- Transparency in Payments (TIP) requirements for FPAC and FPTP data elements; Reporting of alternative payment methods aligned with PSC Resolution 728 on form of payment codes. Changes include the IATA Easypay alternatives (changes have been reflected within DISH Revision 22 Update Bulletin 2018/1);

- New data elements and RET/HOT records to support Complex Taxes Fees and Charges–Additional Coupon Tax Data;

- New data elements and RET/HOT records to support GST related information;

- CSI file format defined as a Mandatory layout for card transactions;

- Complete revision of Testing/Certification Procedures and RET/HOT Data Quality Assurance in DISH Chapter 4;

- Exempted taxes reflected within the TMFA & TMFT data elements;

- New Diners/Discover and JCB specifications to the FPTI data element;

- Addition of other new data element indicators related to Change of Gauge, Commission Control Adjustment, Arrival Date, Arrival Time, Departure Terminal and Arrival Terminal;

- Mandatory/Conditional Status modifications to records and fields in alignment to PSC & Ticketing Resolutions;

- Correction of CSI and CSP data elements status anomalies

A summary of the DISH23.0 changes compared to previous version can be found in the below attached file:

This document identifies all the added and amended records and elements in the new DISH23 reporting capabilities for all the files and transactions in scope. For each new/added DISH element, it is defined the reporting capability and the associated business function and/or amendment along with some comments. This is carried out for all files in scope (RET/HOT/CSI/CSP/TI), records and transactions. The attached DISH23 table is intended for all the business partners to identify very quickly those changes in the DISH23 compared with previous versions

IATA´s approach to DISH23.0 implementation

Full E2E (End to End) testing shall be performed during the pilot Phase 1. A first phase with two pilot waves with 5 BSPs each and one pilot wave with 2 BSPs will serve for testing and official sign-off of the new DISH23.0 reporting capabilities. A second phase for the implementation of DISH23.0 with four waves for the remaining BSPs. A high-level description of the implementation approach is showed below:

In phase 1, parallel test environment shall be used to validate the new DISH23.0 reporting capabilities for the files In-Scope (RET/HOT/CSI).

Note: Pilot Wave 3 has been delayed due to IBSPS project implementation in DPC (this is the software version required prior DISH23 migration)

DISH23.0 implementation Team

A dedicated DISH23.0 Implementation Team has been appointed within IATA FDS division to coordinate DISH23.0 Implementation on its behalf. As such, all DISH23.0 related communications should be channeled through the dedicated IATA DISH23.0 Implementation Team and the assigned DISH23@iata.org mailbox.

Partners/Stakeholders In-Scope

The following parties are considered stakeholders for the purposes of DISH23 project:

- Agents (currently receiving DISH-based Agent HOTs)

- Airlines (Receiving DISH HOT, DISH CSI and CSP files and submitting Refund Notice RETs to the BSPlink and Direct Sales RETs optionally to Weblink and NDCLink)

- Credit Card Acquirers (currently receiving DISH CSI files) known as DISH acquirers

- Credit Card Acquirers (currently receiving local/proprietary files) known as non-DISH acquirers

- GDSs and Local TSPs (sending DISH- RET/TI files to the IATA DPCs)

- IATA Data Processing Centers (DPCs) -receiving RET/TI files and sending HOT/CSI files)

Below there is a flow summary of files and stakeholders in-scope.

Note 1: It is a responsibility of every party receiving HOT or CSI file to ensure that that their downstream systems are capable of processing DISH23 format

Note 2: CSP files described in the DISH are not actually produced by IATA BSPs. However, some parties (like UATP/ATCAN) create output CSP files. If your company is currently receiving DISH22 CSP file, kindly check with the provider if it will be updated to DISH23 format.

Pilot Test BSPs

Pilot Test BSPs

To ensure that most of the Business Partners are involved in the E2E test process of new DISH23.0 reporting capabilities in various areas and systems, 12 BSPs have been selected. The Pilot BSPs span across each IATA Region, cover all Global Reporting Systems and most of the local TSPs, as well all IATA DPC and DPC software provider. The table below shows a relation matrix of BSPs, Regions, DPCs, IBSPS Software and Global Reporting Systems (GDSs/TSP):

| Country | Region | DPC | Software | ABAC | AGTD | EARS | FLGX | GDSL | SABR | WEBL | EDIS | WSPN | ASD1 | ASD2 | AXSS | ESAV | CMAS | INFI | MINS | RESI | STRA | UALA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CA | AM | ACCA | IBSPS |  | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  | X |
| JP | AP | ACCA | IBSPS |  | X | X | X | X | X | X | X | X |  |  | X |  |  | X | X |  |  | X |
| KR | AP | iDPC | IBSPS | X | X | X |  | X |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
| AU | AP | ACCA | IBSPS |  | X | X | X | X | X | X | X |  |  |  |  |  |  |  | X |  |  |  |
| CN | NA | ACCA | IBSPS |  | X |  |  |  |  | X | X |  | X | X |  |  |  |  | X |  |  |  |
| GR | EU | ACCA | IBSPS |  | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| UK | EU | ACCELYA | IBSPS |  | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| IN | AP | DB | IBSPS | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| RU | EU | MULTICARTA | IBSPS |  | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  | X |  |
| EG | ME | ACCELYA | IBSPS |  | X | X | X | X | X |  |  | X |  |  |  |  |  |  |  |  |  |  |
| ZA | AF | ACCELYA | IBSPS |  | X | X | X | X | X |  |  | X |  |  |  |  |  |  |  |  |  |  |
| BR | AM | ACCELYA | IBSPS |  | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |

All the Reporting Systems showed in the above table will not be required to provide test files to any other BSPs besides the Pilot ones.

Note: ZA (South Africa) and BR (Brazil) are strongly related to migration from Maestro to IBSPS –

Pilot Test Scope

Pilot test in the selected BSPs will be carried out in a test environment in parallel with the processing of DISH22 production RET files and generation of outputs (HOT/CSI).

For the pilot test the following functionalities are out of scope:

- EMV is out of scope in DISH23 (in pilot test and global roll out). At this stage, no GDS/TSP confirmed that they would be reporting IT0D records, so IT0D/BCC83/CAD/IAD records reporting will be out of DISH23 Implementation Project scope

- 3DS is out of scope for the parallel test run (3DS may be tested as a new product/functionality, as applicable)

- Coupon Tax is out of scope, as no Airline/GDS confirmed the capability of reporting Coupon Tax data

All the remaining added/amended records/elements are within pilot test scope when applicable.

Note: DISH23 is related to format change only. Provision of the conditional records/elements will be subject to Airlines/GDSs capability to produce such data in Ticketing or other upper stream systems to be reported by GDSs on the RET file.

Test Plan for Pilot BSPs

Detailed Test Plans for the Pilot BSPs will be created by the DISH23.0 Team and released in due time to the partners involved in the tests. The detailed plans shall contain the following information but not limited to:

- Functionalities to be tested

- Contact Information for each of the partners in scope of the test

- Input Files with names

- Output Files with names

- Transmission Channel

- Schedule

- Test assessment and error logs

For any GDS/TSP wishing to implement 3DS, a separate test will be carried out for the new 3DS reporting capabilities.  Details of these tests will be released in due time once the information has been gathered by the GDSs and it will be included in an Appendix at the end of this document.

Reporting Systems Involvement

Global Reporting Systems Readiness Milestone

By 27th of November 2018, all Global Reporting Systems, as well as local systems in scope, must confirm readiness to start testing DISH23.0 for Pilot BSPs as of 1st of March 2019.

Written readiness confirmation must be sent through the dedicated mailbox assigned to the DISH23.0 project: DISH23@iata.org

Input Test Files per Reporting System

The input test files In-Scope are:

- GDSs and TSPs providing RET and TI files to any of the Pilot BSPs must provide a test DISH23 RET and a test DISH23 TI file. Each test DISH23 RET and TI file must be a parallel of the production DISH22 RET and TI files, therefore containing a representative mix of transaction types.

- Weblink must provide the DISH23 RET files for the testing. It should be noted that the airlines sending input RET files to the Weblink have an option of submitting them in any currently existing format, including non-RETs format. Weblink will create one DISH23 RET per Pilot BSP.

- NDClink must provide the DISH23 RET files for the testing. NDClink will create one DISH23 RET per Pilot BSP. Functionality of DISH23 creation from DISH22 should be already in place for this.

- For BSPlink/ASD, the situation is as follows:

  - For the direct refund loading process, the airlines may submit the RET (“ed” files) to BSPlink either in DISH22 or in DISH23 formats. BSPlink will create RET in DISH23 format to be loaded into the DPC systems.

  - The formats of the ACDM (“ec” files) and refund application (“e9” files) files are outside of DISH specifications and therefore no change is expected in these two files submitted by the airlines

Card Authentication and 3DS Card Authentication Information (IT0D and IT0X Records)

See Appendix A of this document

Test Period (SPED)

Pilot BSPs test shall be split in three waves as per the detailed schedule in Section 13.1.4 of this document. First wave shall last from 01-March-2019 to 20-June-2019, the second wave from 01-April-2019 to 20-July-19 and the third one from 01-May-2019 to 20-July-2019 respectively (for detailed dates, please go to section 13.1.4 of this document).

The test data to be used will be that of one reporting day only (SPED), and the SPED will depend on the wave the Pilot BSP belongs to:

| Wave | SPED |
| --- | --- |
| Wave 1 | 28th February 2019 |
| Wave 2 | 28th March 2019 |
| Wave 3 | 31st July 2019 |

Test File Naming Convention

All test 23 RET and TI files must also have filenames which clearly identify them as test files and differentiate them from production files.

As per DISH23 Handbook (section 2.3.6), files must have the following naming convention;

| Item | Description | Example |
| --- | --- | --- |
| ISOC | DPC Country Code | DE, GB, IT |
| SPED | YYMMDD | 150625 |
| RPSI | Reporting System Identifier | GDSL, ABAC, STRA |
| SEQ | Sequence 001 - 999 | 001 |
| TYPE | File Type | RET, TID |
| TPST | Test | TEST |

Test File Delivery Method

IATA´s DISH23.0 Implementation Team will agree bilaterally with each Reporting System the method/transmission of the test 23 RET and TI files will be securely delivered for each of the Pilot BSPs. This will be documented as part of the detailed Test Plan for each of these BSPs.

Note: non-secure delivery methods for test files (e.g. email etc.) will not be acceptable under any circumstances

RET/TI Testing Methodology

All efforts will be made to provide to each Reporting System with initial test feedback as defined in the test plan that will be released in due time.

Initial test feedback will be based on the comparison of RET/TI file validation/error reports against the equivalent production reports, which will be fully analysed by the IATA Implementation Team for correctness. This will provide an early indication of any errors with the reporting data, and Reporting Systems will be requested to provide a corrected test file as soon as possible should any error have been identified.

All Input files from Reporting Systems must meet 5 fundamental criteria, to be accepted as DISH 23 compliant, as follows:

- Test Criteria #1 - IT01/TI1-REVN

- IT01/TI1 – REVN must contain “230”

- Test Criteria #2 - IT01/TI1-TPST

- IT01/TI1 – TPST must contain “TEST”

- Test Criteria #3 - IT01/TI1-SPED

- IT01/TI1 – SPED must contain “190228”, “190328” or “190430” depending on the Pilot BSP migration wave

- Test Criteria #4 - Parallel Content

- Each test 23 RET and TI file must be a parallel of the production DISH22 RET and TI file for the same date (as defined in the Section 6.4 of this document), i.e. the same transactions must be included in the files.

- Test Criteria #5 - Detailed Validation

- All data content is to be fully validated by DPC for correctness against DISH 23 standards. Errors and Warnings from the corresponding production files will also be taken into consideration – i.e. any non- compliance DISH 22 errors carried through to DISH 23.0 testing will require an agreed corrective action plan.

DPCs Involvement

DPCs Readiness Milestone

By 27th of November 2018, IATA software providers must confirm readiness to start testing DISH23.0 for Pilot BSPs as of 1st of March 2019.

RET/TI Validation & Processing

Please, refer to section 6 of this document.

Airline HOT Generation

The following tasks must be carried out by the DPCs:

Pilot BSPs

DPCs will create test DISH23.0 HOT files to all airlines. For the pilot BSP test, up to 5 different airlines at each BSP in parallel with production 22 HOT files for the same date will participate in the Sign Off process.

All test HOT files will be identified by the TEST230 to indicate it is a DISH23 test file in the file name. TPST element in the record BFH01 will be set to TEST. This is applicable to both, test partners and rest of partners. A separate communication with the details of the file naming convention for HOT files will be sent.

Test file delivery method for Pilot BSPs test partners will be agreed with each testing airline in scope as part of the Test Plan outlined in section 5.2 of this document.

Test files for non-testing partners will be massively distributed by the DPCs to all current HOT recipients in Pilot BSPs through BSPLink interface. Separate communications to output recipients in each Pilot BSP will be issued prior to test file release with additional information.

Note that sign-offs on test files are only required by test partners.

Non-Pilot BSPs

It is considered that the provision of test files to the 12 selected Pilot BSPs to be sufficient for airline internal testing so no additional test files are planned to be distributed. However, if there is a specific need for a test file in a non-Pilot BSP, please send the request to DISH23.0 Implementation Team through the dedicated mailbox DISH23@iata.org. All requests will be evaluated on a case by case basis.

Airline CSI Generation

The DPCs will create test DISH23.0 CSI files for all airlines who currently receive CSI files in DISH22 formats in both, Pilot and non-Pilot BSPs. Note that only one airline CSI recipient in a Pilot BSP is required to sign-off on the test files.  The test files for non-Pilot BSPs will only be intended for airline internal testing and not for sign-off purposes.

TPST element in CFH record will be set to TEST.

Note: CSP files described in the DISH are not actually produced by IATA BSPs. However, some parties (like UATP/ATCAN) create output CSP files. If your company is currently receiving DISH22 CSP file, kindly check with the provider if it will be updated to DISH23 format.

Card Acquirers CSI Generation

DPCs will create test DISH 23.0 CSI files for all Credit Card Acquirers (CCA) who currently receive CSI or non-CSI files in both, Pilot and non-Pilot BSPs. Note that only one CCA CSI recipient in a Pilot BSP is required to sign-off on the test files. The test files for non-Pilot BSPs will only be intended for acquirer internal testing and not for sign-off purposes.

The test CSI filenames and distribution channel will be communicated and determined with each acquirer individually. The TPST element in the CFH record will be set to TEST.

Agent HOT Generation

Upon request by a BSP Airline, the DPC prepares an electronic file known as the Airline Accounting/Sales Data or HOT. This contains all accountable transactions from all agents in a BSP, for an agreed period, for each BSP Airline. The DPC also prepares Agent HOT and Agent Group HOT based on this standard airline HOT.

The agent file is deemed to be a standard HOT if it matches the following criteria:

- The file format follows the structure of the standard airline HOT described in DISH22 or lower release

- File contains the data for an agent or the group of agents. TACN element in the BFH/01 record is therefore defaulted to blank

The recipients of the files matching the above criteria must be upgraded to the DISH23.0 version. Agents receiving files in any other format are not mandated to migrate to DISH 22.0 within the scope of this Project.

Note1: IATA strongly recommends those agents who currently receive non-DISH based outputs to consider the possibility of updating their systems to accept standard agent HOTs in order to benefit from the most complete, consistent and always up to date industry format

Note2: If the above criteria are still not clear, agents are encouraged to submit further queries to DISH23@iata.org mailbox.

DPCs will create test 23.0 HOT files for all agents who currently receive standard DISH-based HOT file in both Pilot BSPs as well as non-Pilot BSPs. Note that sign-offs on test files are only required by one testing agent per Pilot BSP.

The test HOT files will be identified by the TEST_230 prefix in the file name. The TPST element in the BFH01 record will be set to TEST.

Airlines Involvement

HOT files testing

Up to a maximum of 5 testing airlines per Pilot BSP will participate in the DISH23.0 HOT testing and Sign-Off.

|  |  |  |  |  | DISH23.0 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wave | Country | Airline 1 | Airline 2 | Airline 3 | Airline 4 | Airline 5 | Airline 6 | Airline 7 | Airline 8 |
| 1 | Canada | LH | KL | AM | AC | S7 | PD | EY | VA |
| 1 | Japan | AM | S7 | EK | VA |  |  |  |  |
| 1 | Korea | NZ | BA | SQ | SU | EK | OZ | VA |  |
| 1 | Australia | NZ | SU | VA |  |  |  |  |  |
| 1 | China | LH | NZ | BA | SQ | AM | EY | VA |  |
| 2 | Greece | LH | IB | S7 | CY |  |  |  |  |
| 2 | United Kingdom | BA | NZ | KL | IB | AM |  |  |  |
| 2 | India | LH | NZ | AC | EK | EY |  |  |  |
| 2 | Russia | OK | NZ | SQ | SU | IB |  |  |  |
| 2 | Egypt | RJ | IB | EK |  |  |  |  |  |
| 3 | South Africa | KL | RJ | AC |  |  |  |  |  |
| 3 | Brazil | LH | BA | SQ | IB | AM |  |  |  |

Please note that all airlines currently receiving HOTs in the Pilot BSPs will be provided one test file per Pilot BSP for their internal system testing. However, the sign-off on the HOT files is only expected from the Testing Airlines.

Note: If you are an airline willing to participate in the pilot BSP test, please contact DISH23 team at: DISH23@iata.org

The following criteria will be used for HOT test acceptance (applicable to test partners):

- Test Criteria #1 – Total Remittance Amount

- Total Remittance Amount (TREM) in production and test HOTs should match (excluding any known differences communicated in advance by IATA Implementation Project Manager).

- Test Criteria #2 – Detailed Validation

- All HOT data content should be compliant to DISH23.0 specifications

Airline CSI files testing

All airlines currently receiving DISH22 CSI files will be provided with the DISH23.0 CSI test file.

The following criteria are established for the CSI testing (applicable to the Airline CSI sign off partner(s) at each BSP):

- Test Criteria #1 – Total Amounts

- Total Amounts (FLDE/FLCR) in production and test CSI files should match (excluding any known differences communicated in advance by IATA Implementation Project Manager).

- Test Criteria #2 – Detailed Validation

- All CSI data content should be compliant to DISH23.0 specifications

RET files from Airlines (WebLink)

Please refer to the section 6.2 of this document.

RET files from Airlines (NDCLink)

Please refer to the section 6.2 of this document.

Acquirers Involvement

Acquirers CSI files testing

All acquirers irrespective of the current format use will be provided with the test DISH23.0 CSI file.

The following criteria is established for the CSI testing (applicable to the Acquirer CSI sign off partner(s) at each BSP):

- Test Criteria #1 – Total Amounts

- For DISH CSI files, total Amounts (FLDE/FLCR) in production and test CSI files should match (excluding any known differences communicated in advance by IATA Implementation Project Manager).

- For non-DISH CSI files, total Amounts in production and test CSI files should match (excluding any known differences communicated in advance by IATA Implementation Project Manager).

- Test Criteria #2 – Detailed Validation

- All CSI data content should be compliant to DISH23.0 specifications

Note1: It should be stressed that Card Acquirers who are currently receiving non-CSI Credit Card Billing formats have the following options for the processing of non-DISH versions:

- Upgrade their systems to process DISH23 CSI file format

- Outsource the service of processing DISH23 CSI files produced by DPCs to third parties (Processors) for the purpose of converting them into specific format required by the card acquirer

Note2: If you are an acquirer currently receiving non-DISH23 CSI file format or lower DISH CSI file versions and requires a grace period for adopting the system to the DISH23 requirements, please inform us in written to the dedicated mailbox: DISH23@iata.org by 30th September 2018 the latest. In this case, IATA shall provide a temporary and chargeable option for a maximum period of six-months, ending June 2020, and with the following terms and conditions:

  - Acquirer must enter contractual relationship with IATA by 31st December 2018 the latest. Without a contractual relationship IATA shall not provide the current service of sending local/proprietary files or CSI lower file versions to DISH23, effective 1st January 2020. The contract will be effective as of 1st January 2020 until 30th June 2020

  - After the interim period of six-months (from 1st January 2020 until 30th June 2020) the services shall be discontinue by IATA and only DISH23 CSI files shall be delivered

  - During the interim period of six-months (from 1st January 2020 until 30th June 2020) IATA shall not take any development on the file format in use by the card acquirer, i.e. acquirer shall receive the same file with the same format as of today

Note3: For BSP Brazil (BR), IATA is working in the possibility of adding R6069 specifics for installment payments into the CSI file with an additional optional record that will not affect the remaining BSPs. A paper will be presented to BDISG working group in September 2018. The result of the decision will be duly communicated to the acquirers.

Note4: For BSP Korea (KR), IATA is evaluating possible options to get an agreement with all local acquirers.

Note5: By completion of the DISH23 implementation timelines, IATA shall not service non-DISH23 CSI format files´ to any acquirer.

Agents Involvement

Agent HOT files testing

(Please also refer to Section 7.6 on this document)

All acquirers currently receiving standard DISH-based HOT files will be provided with the DISH 23.0 test HOT file.

The following criteria are established for the agent HOTs testing (applicable to the Agent sign off partner(s) in each BSP):

- Test Criteria #1 – Total Remittance Amount

- Total Remittance Amount (TREM) in production and test HOTs should match (excluding any known differences communicated in advance by IATA Implementation Project Manager).

- Test Criteria #2 – Detailed Validation

- All HOT data content should be compliant to DISH23.0 specifications

Third Parties Involvement

The following activities are planned by IATA to involve third parties into the DISH23.0 Implementation:

- Major Revenue Accounting System providers will be contacted to assure that their systems are capable of processing DISH23.0 outputs.

- ATPCO is contacted to make sure that the DISH23.0 HOT files can be processed by ATPCO’s Airline Sales Exchange.

- All possible support and information will be given to other third parties who will be in contact with IATA for the DISH23.0 Implementation. Airlines and Agents may encourage their providers/third party to contact DISH23 Team directly should they need any technical clarification

IATA Involvement

DISH 23.0 Implementation Team has been formed within the IATA FDS division to coordinate the DISH23.0 Implementation on behalf of IATA. As such, all DISH23.0 related communications should be channeled through IATA DISH23.0 Implementation Team, contact details as follows:

Project Manager

Jaime Pandavenes

Email: DISH23@iata.org

Mobile: +34 66 012 79 10

Assistant Project Manager

Gustavo Carballo

Email: DISH23@iata.org

Assistant Project Manager

Haya Ajeilat

Email: DISH23@iata.org

IATA regional offices will be involved in the DISH23.0 project especially for communication to the local business partners.

Implementation Schedule

Milestones and Timelines

BSPs DISH23.0 implementation is divided into 2 phases as described in section 3 of this document. There will be 12 BSPs for the Pilot Test and the remaining BSPs will be distributed in four waves.

Testing Process

A high-level description of the testing process is showed below:

Sign-Off Date and Go/No-Go Decision

IATA will not provide a 23.0 signoff statement until the resulting test outputs have been signed off by the test partners, or any differences with test outputs have been verified as not being attributed to a RET reporting problem for that Reporting System.

To give the green light (Go decision) to a Pilot BSP:

- All testing airlines must provide their sign-off for the HOT file

- At least one agent should provide their sign-off on the Agent HOT

- At least one card acquirer must provide their sign-off on the CSI file

- At least one airline must provide their sign-off on the CSI file

Regarding Implementation dates, IATA Implementation Team will communicate a Go (green light) or No-Go (red light) decision to all business partners in all BSPs two weeks in advance. Any No-Go (red light) decisions taken will result in the Implementation date for that BSP to be rescheduled later.

Implementation Date

Once the IATA Implementation Team has given a Go (green light) decision to implement DISH 23.0 in any BSP, all System Providers must implement 23.0 on the exact day specified in the Implementation Schedule. DPCs will not accept or process any RET or TI production file in any revision other than 23.0, after the confirmed 23.0 Implementation date per BSP.

All implementation dates reflect the date of issuance of transactions within the first RET and TI file to be sent in 23.0 (i.e. SPED)

Factors taken into consideration for the implementation dates included:

- must be on the 1st of the month

- must be on the first day of any BSP billing period

- must not be during or immediately preceding a weekend

- must not be during or immediately preceding a major public holiday

Pilot BSPs

Key project milestones for the Pilot BSPs are showed below:

| DISH23.0 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wave | Pilot BSP | Test Date (SPED) | Deliver test RET & TI files by TSP | RET/TI Pre-approval by DPC | Outputs Submission to Testing Partners | Sign-Off by Testing Partners & IATA | Go/No-Go Decision Date | Go Live (SPED) |
| 1 | CANADA | 28-Feb-19 | 06-Mar-19 | 05-Apr-19 | 11-Apr-19 | 10-Jun-19 | 17-Jun-19 | 02-Jul-19 |
| 1 | JAPAN | 28-Feb-19 | 06-Mar-19 | 05-Apr-19 | 11-Apr-19 | 10-Jun-19 | 17-Jun-19 | 02-Jul-19 |
| 1 | KOREA | 28-Feb-19 | 06-Mar-19 | 05-Apr-19 | 11-Apr-19 | 10-Jun-19 | 17-Jun-19 | 02-Jul-19 |
| 1 | AUSTRALIA | 28-Feb-19 | 06-Mar-19 | 05-Apr-19 | 11-Apr-19 | 10-Jun-19 | 17-Jun-19 | 02-Jul-19 |
| 1 | CHINA | 28-Feb-19 | 06-Mar-19 | 05-Apr-19 | 11-Apr-19 | 10-Jun-19 | 17-Jun-19 | 02-Jul-19 |
| 2 | GREECE | 28-Mar-19 | 04-Apr-19 | 07-May-19 | 10-May-19 | 09-Jul-19 | 18-Jul-19 | 02-Aug-19 |
| 2 | UNITED KINGDOM | 28-Mar-19 | 04-Apr-19 | 07-May-19 | 10-May-19 | 09-Jul-19 | 18-Jul-19 | 02-Aug-19 |
| 2 | INDIA | 28-Mar-19 | 04-Apr-19 | 07-May-19 | 10-May-19 | 09-Jul-19 | 18-Jul-19 | 02-Aug-19 |
| 2 | RUSSIA | 28-Mar-19 | 04-Apr-19 | 07-May-19 | 10-May-19 | 09-Jul-19 | 18-Jul-19 | 02-Aug-19 |
| 2 | EGYPT | 28-Mar-19 | 04-Apr-19 | 07-May-19 | 10-May-19 | 09-Jul-19 | 18-Jul-19 | 02-Aug-19 |
| 3 | South Africa | 31-July-19 | 08-Aug-19 | 22-Aug-19 | 22-Aug-19 | 09-Sep-19 | 17-Oct-19 | 02-Dec-19 |
| 3 | BRAZIL | 31-July-19 | 08-Aug-19 | 22-Aug-19 | 22-Aug-19 | 09-Sep-19 | 17-Oct-19 | 04-Nov-19 |

Sign-Off, Go-No-Go and implementation dates are in line with the process and timelines described in section 13.1.1 and 13.1.2 of this document.

- The first 5 BSPs in Wave 1 should Go Live by 01st of July

- The second 5 BSPs in Wave 2 should Go Live by 01st of August

- The third 2 BSPs in Wave 3 should Go Live by 04th of November and 02nd of December respectively

Global Roll-Out BSPs

After successful testing and implementation of the DISH 23.0 in the Pilot BSPs, IATA will coordinate the implementation in all Other BSP countries. The implementation of the non-Pilot BSPs is split into 4 waves in accordance considering IBSPS migration timelines. Below you can find a detailed list of the BSPs for each of the waves:

APPENDIX A: 3DS TEST

“To be tested independently as a new “product/functionality” as per DISH23 chapter 4.3.3 and within a DISH23 environment. Details to be provided in a later stage”

3DS stands for 3 Domain Secure (Merchant-Airline, Acquiring Bank and Card Issuer), a protocol designed to be an additional security layer for online credit and debit card transactions. 3DS requires that the credit card holder directly input their payment info via an online interface. Major benefits of using 3DS technology are fraud deterrent and liability shift from the Airline to the Card Issuer.

Travel Agents must have the ability to issue such transactions through the GDSs:

- GDSs and Agents must upgrade their current interaction:

  - Agents must be able to perform cardholder authentication request and pass the result to the GDSs

  - GDSs must be able to receive the result of cardholder authentication request and to add it to the "regular/standard" authorization request

A schematic flow diagram below shows the interaction of all participants in the 3DS data flow:

Some GDS/TSP already confirmed that they create the functionality to authenticate 3DS transactions and report them using a fixed length element approach (IT0X record). Credit Card Acquirers may expect CAX records on their files

To certify compliancy with these new records, separate files containing IT0X records will be provided to each BSP if/when applicable.

At Functionality level both WEBLink and NDCLink are the same

Exception being for weekly (Monday to Sunday) billing frequency BSPs, i.e. most of Americas region and some of Asia Pacific region